## Summary
Library Management Application - Development Estimation
Project | Organization-wide Library Management Application
Document Date | June 24, 2026
Team Size | 1 Developer
Development Tool | Cursor AI Assisted Development
Working Hours Per Day | 8 hours
Total Project Duration | 4-5 Working Days
Total Estimated Hours | 40 hours (5 days) / 32 hours (4 days minimum)
Metric | Value
Total Hours (Recommended) | 40
Total Days (Recommended) | 5
Minimum Viable Hours | 32
Minimum Viable Days | 4
Owner | Developer

## Day-wise Detailed Plan
Day | Step # | Time Block | Start Time | End Time | Duration (Hrs) | Module | Task (Detailed) | Deliverable | Owner | Status
Day 1 | 1 | Morning | 09:00 | 11:00 | 2 | Requirement Analysis | Review and validate business requirements with client; confirm in-scope libraries and notification schedule | Validated requirement baseline | Developer | Planned
Day 1 | 2 | Morning | 11:00 | 12:00 | 1 | Requirement Analysis | Finalize BRD, FRS, user stories, and use cases documentation | BRD, FRS documents | Developer | Planned
Day 1 | 3 | Midday | 13:00 | 15:00 | 2 | Database Design | Design data model for Library, Version, Release Notes, Recommendation, Notification entities; map existing DB library records | Data requirement document, Data model | Developer | Planned
Day 1 | 4 | Midday | 15:00 | 16:00 | 1 | Design | Design application workflow (7 steps: DB read, scrape, aggregate, compare, recommend, email, Teams) | Workflow documentation | Developer | Planned
Day 1 | 5 | Afternoon | 16:00 | 18:00 | 2 | Backend Development | Set up project structure; implement database connection; develop read integration for existing library records (version, information notes) | Database integration module | Developer | Planned
Day 2 | 6 | Morning | 09:00 | 12:00 | 3 | Library Scraper | Develop pull/scrape module to retrieve latest library version from external sources | Library scraper module (version) | Developer | Planned
Day 2 | 7 | Morning | 12:00 | 13:00 | 1 | Library Scraper | Extend scraper to pull/scrape release notes for latest version | Release notes retrieval | Developer | Planned
Day 2 | 8 | Midday | 13:00 | 15:00 | 2 | Library Scraper | Support multiple library sources across organization applications | Multi-library scraper support | Developer | Planned
Day 2 | 9 | Afternoon | 15:00 | 17:00 | 2 | Comparison Logic | Develop aggregation logic to combine database records with externally retrieved library data | Aggregation module | Developer | Planned
Day 2 | 10 | Afternoon | 17:00 | 18:00 | 1 | Comparison Logic | Develop version comparison logic to detect whether a new version has been released | Version comparison module | Developer | Planned
Day 3 | 11 | Morning | 09:00 | 11:00 | 2 | Recommendation Engine | Develop upgrade vs. existing version sufficient assessment logic | Upgrade assessment module | Developer | Planned
Day 3 | 12 | Morning | 11:00 | 13:00 | 2 | Recommendation Engine | Develop pros and cons generation for upgrading to new version | Upgrade pros/cons generator | Developer | Planned
Day 3 | 13 | Midday | 13:00 | 15:00 | 2 | Recommendation Engine | Develop pros and cons generation for not upgrading (remaining on current version) | No-upgrade pros/cons generator | Developer | Planned
Day 3 | 14 | Afternoon | 15:00 | 17:00 | 2 | Backend Development | Develop core backend services and scheduled workflow execution trigger | Backend services, Scheduler | Developer | Planned
Day 3 | 15 | Afternoon | 17:00 | 18:00 | 1 | Backend Development | Integrate all modules: DB read, scraper, aggregation, comparison, recommendation into workflow pipeline | Integrated workflow pipeline | Developer | Planned
Day 4 | 16 | Morning | 09:00 | 11:00 | 2 | Email Integration | Configure email service; implement regular email notification with library comparison and recommendation content | Email notification module | Developer | Planned
Day 4 | 17 | Morning | 11:00 | 13:00 | 2 | Teams Integration | Configure Teams group; implement regular Teams group post with library comparison and recommendation content | Teams notification module | Developer | Planned
Day 4 | 18 | Afternoon | 13:00 | 16:00 | 3 | UI Development | Develop UI views to display library status, version comparison results, and upgrade recommendations with pros/cons | Application UI | Developer | Planned
Day 4 | 19 | Afternoon | 16:00 | 18:00 | 2 | UI Development | Develop UI for notification history and scheduled run status display | Notification status UI | Developer | Planned
Day 5 | 20 | Morning | 09:00 | 11:00 | 2 | Testing | Execute unit testing for scraper, comparison, recommendation, and notification modules | Unit test results | Developer | Planned
Day 5 | 21 | Morning | 11:00 | 13:00 | 2 | Testing | Execute integration and end-to-end testing: DB read -> scrape -> compare -> recommend -> email & Teams notify | Integration test results | Developer | Planned
Day 5 | 22 | Afternoon | 13:00 | 15:00 | 2 | Deployment | Environment setup; deploy application to target environment; verify scheduled run | Deployed application | Developer | Planned
Day 5 | 23 | Afternoon | 15:00 | 17:00 | 2 | Documentation | Finalize user documentation and project handover documentation | Final documentation | Developer | Planned
Day 5 | 24 | Afternoon | 17:00 | 18:00 | 1 | Deployment | Client handover, demo walkthrough, and sign-off | Project sign-off | Developer | Planned
TOTAL |  |  |  |  | 44
Day-wise Hour Summary
Day | Total Hours
Day 1 | 8
Day 2 | 9
Day 3 | 9
Day 4 | 9
Day 5 | 9

## Module Estimation
# | Phase | Module | Task | Estimated Hours | Owner | Day | Deliverable
1 | Phase 1 | Requirement Analysis | Review and validate business requirements | 2 | Developer | Day 1 | Validated requirement baseline
2 | Phase 1 | Requirement Analysis | Document BRD, FRS, user stories | 2 | Developer | Day 1 | Requirement documentation
3 | Phase 2 | Database Design | Design data model and map existing DB library records | 2 | Developer | Day 1 | Data requirement document
4 | Phase 2 | Design | Design application workflow and notification approach | 1 | Developer | Day 1 | Workflow documentation
5 | Phase 3 | Backend Development | Develop database read integration for existing library records | 2 | Developer | Day 1 | Database integration module
6 | Phase 3 | Library Scraper | Develop pull/scrape for latest version and release notes | 4 | Developer | Day 2 | Library scraper module
7 | Phase 3 | Library Scraper | Support multiple library sources | 2 | Developer | Day 2 | Multi-library support
8 | Phase 3 | Comparison Logic | Develop aggregation logic combining DB and external data | 2 | Developer | Day 2 | Aggregation module
9 | Phase 3 | Comparison Logic | Develop version comparison to detect new releases | 1 | Developer | Day 2 | Comparison module
10 | Phase 3 | Recommendation Engine | Develop upgrade vs. sufficient assessment logic | 2 | Developer | Day 3 | Upgrade assessment module
11 | Phase 3 | Recommendation Engine | Develop pros and cons generation for upgrade and no-upgrade | 4 | Developer | Day 3 | Recommendation module
12 | Phase 3 | Backend Development | Develop core services and scheduled workflow | 3 | Developer | Day 3 | Backend services
13 | Phase 3 | Email Integration | Configure and implement regular email notification | 2 | Developer | Day 4 | Email module
14 | Phase 3 | Teams Integration | Configure and implement regular Teams group post | 2 | Developer | Day 4 | Teams module
15 | Phase 3 | UI Development | Develop views for library status, comparison, and recommendations | 5 | Developer | Day 4 | Application UI
16 | Phase 4 | Testing | Unit, integration, and end-to-end workflow testing | 4 | Developer | Day 5 | Test results
17 | Phase 5 | Deployment | Environment setup and deployment | 2 | Developer | Day 5 | Deployed application
18 | Phase 5 | Documentation | User and project documentation | 2 | Developer | Day 5 | Final documentation
|  | TOTAL |  | 44

## Phase Summary
Phase | Task | Deliverable | Owner | Duration (Days) | Duration (Hours)
Phase 1 - Requirement Analysis | Review and validate business requirements with client | Validated requirement baseline | Developer | 0.5 | 4
Phase 1 - Requirement Analysis | Finalize BRD, FRS, user stories, use cases | Requirement documentation | Developer | 0.5 | 4
Phase 2 - Design | Design data model and database integration | Data requirement document | Developer | 0.5 | 4
Phase 2 - Design | Design application workflow and notification approach | Workflow documentation | Developer | 0.5 | 4
Phase 3 - Development | Develop database read for existing library records | Database integration module | Developer | 0.5 | 4
Phase 3 - Development | Develop library pull/scrape for version and release notes | Library scraper module | Developer | 1 | 8
Phase 3 - Development | Develop aggregation and version comparison logic | Comparison module | Developer | 0.5 | 4
Phase 3 - Development | Develop recommendation engine (upgrade/sufficient, pros/cons) | Recommendation module | Developer | 1 | 8
Phase 3 - Development | Develop email and Teams notification integration | Notification modules | Developer | 0.5 | 4
Phase 3 - Development | Develop UI and backend scheduled execution | Application UI and backend | Developer | 1 | 8
Phase 4 - Testing | Unit, integration, and end-to-end testing | Test results and sign-off | Developer | 0.5 | 4
Phase 5 - Deployment | Deploy application and finalize documentation | Deployed application and docs | Developer | 0.5 | 4
TOTAL |  |  |  | 7.5 | 60

## 4-Day Alternative
Day | Focus Area | Key Tasks | Hours | Owner | Deliverables
Day 1 | Requirements + Design + DB Integration | Validate requirements; design data model and workflow; implement database read integration | 8 | Developer | BRD, FRS, Data model, DB integration module
Day 2 | Scraper + Comparison | Build pull/scrape for version and release notes; aggregation and version comparison logic | 8 | Developer | Scraper module, Aggregation module, Comparison module
Day 3 | Recommendation + Backend + Notifications | Recommendation engine with pros/cons; backend scheduler; email and Teams integration | 8 | Developer | Recommendation module, Backend, Email & Teams modules
Day 4 | UI + Testing + Deployment | Application UI; unit and E2E testing; deployment and documentation handover | 8 | Developer | UI, Tested & deployed application, Documentation
TOTAL |  |  | 32